## Overview
ZeroShield AI — Project Decision Log & Experiment Registry
Purpose: maintain traceable project decisions and reproducible experiment records for the ZeroShield AI FYP.
Workbook Section | How to Use | Recommended Rule | Meaning
Decision Log | Record important technical, research, scope, dataset and architecture decisions as soon as they are made. | Accepted decision | A choice currently adopted for the project.
Experiment Registry | Create one row before each experiment and update it after execution with results, artefact paths and conclusions. | Revisit | A decision that may need review after pilot evidence.
Decision Evidence | Use repository paths, report sections, meeting notes, issue links or commit hashes as evidence. | Completed experiment | Executed, results recorded and evidence saved.
Experiment IDs | Use a consistent format such as EXP-001, EXP-002, EXP-003. | Do not overwrite | Create a new row if a decision changes, preserve the original record.
Decision IDs | Use a consistent format such as DEC-001, DEC-002, DEC-003.
This workbook supports reproducibility, supervisor review and final-report evidence.

## Decision Log
Decision ID | Date | Category | Decision / Question | Options Considered | Final Decision | Rationale / Evidence | Impact on Project | Status | Owner | Review Trigger / Date | Evidence / Repository Reference
DEC-001 | 2026-08-29 | Research | How should previously unseen threats be described? | Zero-day detection; unknown attack detection; previously unseen threat behaviour | Use 'previously unseen threat behaviour', 'unknown' and 'novelty' where academically supported. | Avoids overstating universal zero-day detection and matches the research framing. | Affects proposal wording, literature review, experiment labels and evaluation claims. | Accepted | Student | Revisit only if supervisor requests a terminology change | docs/literature-review/
DEC-002 | 2026-08-29 | Architecture | Which core detection components should form the baseline? | Suricata + XGBoost + Isolation Forest; deeper open-set models | Use Suricata, XGBoost and Isolation Forest as the core lightweight baseline. | Provides distinct signature, supervised and novelty evidence while keeping scope reproducible. | Defines core backend modules and the experiment sequence. | Accepted | Student | Revisit if baseline evidence shows a specific limitation | docs/architecture/
DEC-003 | 2026-08-29 | Dataset | Which dataset should be used first? | DataSense CIC IIoT 2025; TabularIoTAttack-2024; CIC-YNU-IoTMal 2026 | Pilot DataSense CIC IIoT 2025 first; keep TabularIoTAttack-2024 as fallback. | Selection remains provisional until accessibility, labels, class structure and withheld-class feasibility are checked. | Controls dataset feasibility work and experiment planning. | Accepted | Student | After dataset feasibility pilot | data/README.md
DEC-004 | 2026-08-29 | Response Safety | Should novelty detection automatically block traffic? | Automatic containment; recommendation only; human-approved temporary containment | Require human approval for potentially disruptive temporary containment. | Novelty evidence is uncertain and false positives could disrupt legitimate activity. | Defines dashboard workflow, audit logging, timeout and rollback requirements. | Accepted | Student | Revisit only after validated response testing | docs/architecture/01_System_Boundary_and_Assumptions_ZeroShield_AI.docx
DEC-005 | 2026-08-29 | Scope | Should deep open-set models be part of the core implementation? | Autoencoder; Deep SVDD; One-Class SVM; classical lightweight baseline | Keep advanced deep models optional unless pilot evidence justifies them. | Prevents scope creep and preserves feasibility on modest hardware. | Keeps the core FYP focused on the minimum model set needed to answer the research question. | Accepted | Student | After baseline novelty experiment | docs/literature-review/

## Experiment Registry
Experiment ID | Experiment Name | Research Purpose / Hypothesis | Dataset / Traffic Source | Training Knowledge | Test Condition | Model / Tool | Config / Version | Features / Preprocessing | Withheld Class / Leakage Control | Primary Metrics | Threshold / Operating Point | Start Date | End Date | Status | Result Summary | Key Metrics / Outcome | Conclusion / Decision | Artefact / Output Path | Commit / Tag / Evidence
EXP-001 | Signature Baseline | Establish deterministic known-threat detection baseline. | Selected dataset / replayed lab traffic | Suricata ruleset only | Known attacks detectable by rules | Suricata | Record ruleset and Suricata version | Record telemetry format and parsing steps | N/A | Detection rate, FPR, latency | To be validated |  |  | Planned |  |  |  | experiments/signature_baseline/
EXP-002 | Known-Class ML Baseline | Measure closed-set classification performance for trained attack classes. | Selected tabular dataset | Normal + selected known attack classes | Held-out records from the same known classes | XGBoost | Record package/model parameters | Document feature schema, encoding, scaling and split | No withheld-class samples in this experiment | Accuracy, macro precision/recall/F1, per-class recall, FPR, latency | To be validated |  |  | Planned |  |  |  | experiments/known_class/
EXP-003 | Withheld-Class Novelty | Test detection of attack behaviour absent from model development. | Selected tabular dataset | Normal/known reference data with one attack class excluded | Introduce excluded attack class only at test time | Isolation Forest | Record contamination, seed and model version | Document preprocessing; fit only on permitted reference data | Withheld class excluded from training, validation, feature selection and threshold calibration | Unknown recall, FPR, threshold curve, latency | Threshold selected using validation only |  |  | Planned |  |  |  | experiments/withheld_class/
EXP-004 | Hybrid Evidence Correlation | Assess whether combining distinct detector evidence improves useful coverage without unacceptable false-positive noise. | Aligned outputs from baseline experiments | Outputs from Suricata, XGBoost and Isolation Forest | Aligned test stream / records | Evidence Correlation Layer | Record correlation policy version | Use detector-specific outputs without converting them into equivalent probabilities | Do not tune fusion using withheld-class labels | Coverage, FPR, conflict cases, latency | Policy validated on permitted validation data |  |  | Planned |  |  |  | experiments/hybrid_fusion/
EXP-005 | Explanation and Response Traceability | Evaluate whether detector-specific evidence supports safe human-approved temporary containment. | Validated incidents from hybrid experiment | Validated detector evidence | Analyst-facing incident records | SHAP + novelty evidence + response workflow | Record explanation/response component versions | Known-class: SHAP; novelty: anomaly score, threshold and feature deviations | No automatic disruptive response from novelty evidence alone | Traceability completeness, response correctness, rollback/audit completeness | Approved policy only |  |  | Planned |  |  |  | experiments/explanation_response/